## Slide 1
Classification of Malignant Melanoma in Canines
@reallygreatsite
Week 1–2 Progress — Foundation Phase
Muhammad Tayyab Abbas · MSc AI & Data Science · University of Hull
Supervisor: Dr Claire Cashmore · 1st fortnightly meeting

## Slide 2
12-week project: 26 May → 14 Aug 2026, submission 17 Aug 2026.
Where we are in the plan

## Slide 3
On schedule.
Planned vs. done (Gantt)

## Slide 4
1 · Environment setup ✓
  Isolated virtual environment (.venv) — other projects untouched
  Python 3.12 + OpenCV, scikit-image, scikit-learn, OpenSlide (PyTorch next)
  Reproducible: requirements.txt + requirements-lock.txt + setup_env scripts
  Clean modular src/ package, version-controlled (Git)

## Slide 5
2 · Literature review refined ✓
  Segmentation: U-Net (Ronneberger 2015), Attention U-Net (Oktay 2018)
  Classification: ResNet-50 (He 2016), EfficientNet-B3 (Tan & Le 2019)
  Preprocessing: Macenko stain normalisation (2009)
  Interpretability: Grad-CAM (Selvaraju 2017)
  Comparative oncology: Gillard (2014), Prouteau & André (2019)

## Slide 6
3 · Preprocessing pipeline — built & validated ✓
  Quality check flags blurry / low-tissue / washed-out slides automatically
  Macenko removes scanner/lab colour variation
  Only tissue patches (≥50%) are kept
  Stratified split preserves class balance
Whole-slide image → QA → Macenko normalise → patch extraction → 70/15/15 split

## Slide 7
Result — stain normalisation (before / after)

## Slide 8
Result — extracted tissue patches

## Slide 9
Pipeline runs end-to-end and is ready to run unchanged on the real CATCH slides once the TCIA download completes.
Validation run (synthetic slides)

## Slide 10
Risks & mitigations

## Slide 11
Next fortnight (Weeks 3–5)
  Complete CATCH download → run pipeline on all real slides
  Finalise patch dataset + class statistics
  Start U-Net segmentation (baseline → ResNet-34 encoder)
Questions: QA thresholds OK? · final class list? · magnification priority?

## Slide 12
@reallygreatsite
Thank You
Questions & feedback welcome