# Progress Report — Weeks 3–4 (Model Development: U-Net Segmentation)

Project: Classification of Malignant Melanoma in Canines (CATCH)

Project Code: DAIM2025A_088

Student: Muhammad Tayyab Abbas

Supervisor: Dr Claire Cashmore

Reporting period: Weeks 3–4 (9 – 22 June 2026)

Meeting: Second fortnightly supervisor meeting

# 1. Summary

Phase 2 (Model Development) has begun on schedule. The remaining preprocessing items from Phase 1 were completed (multi-magnification 5x/10x/20x patch extraction and a full augmentation pipeline), and the U-Net tumour-segmentation model has been implemented, trained and evaluated end-to-end. Following the plan, a from-scratch baseline U-Net was trained first, then a U-Net with an ImageNet-pretrained ResNet-34 encoder (transfer learning). Both were validated on synthetic annotated slides while the CATCH download is finalised; the code runs unchanged on the real annotated slides.

# 2. Planned vs. actual

| Gantt task | Planned | Status |
| --- | --- | --- |
| Data Acquisition & Preprocessing | W1–3 | Complete (multi-mag + augmentation added) |
| U-Net Segmentation Development | W3–5 | On track (baseline + ResNet-34 trained, W3–4) |

# 3. What was completed

Multi-magnification patch extraction (5x/10x/20x) with paired image+mask tiling and tissue filtering.

Augmentation pipeline (flips, 90° rotations, elastic deformation, brightness/contrast, H&E hue-saturation jitter) applied to training only.

Segmentation dataset with slide-level train/val/test split (no slide spans two subsets — prevents patch leakage).

U-Net models: from-scratch baseline and ResNet-34-encoder (transfer learning), composite BCE+Dice loss with class-imbalance pos_weight.

Training recipe per proposal: Adam lr=1e-4, cosine annealing, early stopping on val-Dice, TensorBoard logging, best-checkpoint saving.

Evaluation: Dice, IoU, pixel-accuracy and Hausdorff distance on the test split, with training-curve and prediction-overlay figures.

# 4. Results (test split)

| Model | Dice | IoU | Pixel acc. | Hausdorff | Params |
| --- | --- | --- | --- | --- | --- |
| Baseline U-Net | 0.218 | 0.204 | 0.993 | 154.8 | 31.04M |
| U-Net + ResNet-34 | 0.430 | 0.405 | 0.991 | 115.1 | 24.44M |

Note: metrics are from the synthetic validation dataset and demonstrate the pipeline end-to-end; absolute values will change on the real CATCH slides. The proposal target is Dice > 0.85 on real data.

Figure: ResNet-34 U-Net training curves (loss + validation Dice).

Figure: test predictions (image | ground truth | prediction).

# 5. Next fortnight (Weeks 5–6)

Implement the Attention U-Net variant and compare against the ResNet-34 U-Net.

Run the trained pipeline on the real CATCH annotated slides once downloaded.

Begin ResNet-50 classification (Week 6).